## Sheet1
Mousetuary TODO list
1.0.1
Feature/bug | Status | Comments/Issues
Home Screen and widget lists
Sysmenu: minimise, window, exit | Done | Need better handling of maximise from Win titlebar. Bug reported. Once fixed, these buttons can be hidden when windowed.
Back and Home to topbar. | Done
Tidy up text and clock in topbar | Done | Smaller and less shouty text in general.
Remove silly option thing (sidemenu) | Reinstated | Fixed losing focus by using a window property, like Aeon Nox 5 does. Options button up in top bar. Dismiss by a back button.
Sensible defaults | Low priority | Can you control these on a skin-by-skin basis? (like order and enabling of buttons on main menu)
Scroll bars in widget lists | Done | Gives a standard way of scrolling them, since autoscroll is not working consistently. The mouse wheel can be used in the scroll bar (while in the widget rows, it scrolls them horizontally)
Video OSD
OSD pause button flickers when mouse moved | Done | Removed DefaultControl setting - seems to have no ill effects
OSD FF/REW and volume buttons | Done
OSD skip fwd/back buttons | Done | These do Next/Prev for DVD and SmallStepForward/Back for Live TV
OSD transparent background colour nicer | Done | Make it blue like WMC. Also make a semitransparent blue background for the guide when live video is in progress.
Get rid of fwd/back buttons from OSD slider nib | Done
Get rid of misleading message for slider | Done
Use full guide rather than the abbreviated OSD guide. Remove OSD channel button. | Done | Ctrl-g for guide with support of a script (goes with optional keymap)
Live TV widget list
Channels and Guide seem redundant. | Done-ish | Can we just have the Guide and get rid of Channels? For the moment, just make guide the first widget in the line.
Make Guide come first in widget list | Done | Pending decision on the above
TV Guide
Guide should roll up and down with the mouse wheel, not left to right. | Done | Done using a keymap.
Guide needs up/down/left/right buttons that appear with a mouse hover, like WMC | Done
Guide rows need to be a little bigger, also guide font | Done
1.0.2
TV Guide
Provide setting to control genre coloring | Done
Incomplete:
Fix over-aggressive autoscroll in Addons/MyAddons list | Not done | It's awful! It should either autoscroll properly, or have a scroll bar.
VideoOSDHelpTextVar for new buttons (variables.xml) | Started | Display left-side ones on left, if possible.
Right-click option to delete recent channels from list | Not skinnable | There is very limited scope for skins to do this (existing context menus can be added to, but new ones can't be created)
OSD slider can report timeshift buffer extent to scale, like WMC does | Partially done | Done with Python script. Still awaiting bug fix for Player.Progress (bug tracker #17469)