## Sheet1
Mousetuary TODO list
Feature/bug | Status | Comments | Initiator
Home Screen and widget lists
Sysmenu: minimise, window, exit | Done | Need better handling of maximise from Win titlebar. Bug reported. Once fixed, these buttons can be hidden when windowed.
Back and Home to topbar. | Done
Tidy up text and clock in topbar | Done | Smaller and less shouty text in general.
Remove silly option thing (sidemenu) | Reinstated | Fixed losing focus by using a window property, like Aeon Nox 5 does. Dismiss by a back button.
Sensible defaults | Low priority | Can you control these on a skin-by-skin basis? (like order and enabling of buttons on main menu)
Scroll bars in widget lists | Done | Gives a standard way of scrolling them, since autoscroll is not working consistently. The mouse wheel can be used in the scroll bar (while in the widget rows, it scrolls them horizontally) | leon_tamp
Fix over-aggressive autoscroll in Addons/MyAddons list |  | It's awful! It should either autoscroll properly, or have a scroll bar.
Video OSD
OSD pause button flickers when mouse moved | Done | Removed DefaultControl setting - seems to have no ill effects
OSD FF/REW and volume buttons | Done
OSD skip fwd/back buttons | Done | These do Next/Prev for DVD and SmallStepForward/Back for Live TV
OSD transparent background colour nicer
Get rid of fwd/back buttons from OSD slider nib | Done
OSD slider can report timeshift buffer extent |  | Like WMC does. Awaiting a PVR backend that reports this information (NextPVR doesn't)
VideoOSDHelpTextVar for new buttons (variables.xml) | Needs localize | Display left-side ones on left, if possible.
Get rid of misleading message for slider | Done
Use full guide rather than the abbreviated OSD guide. Remove OSD channel button. | Done
Live TV widget list
Right-click option to delete recent channels from list |  | More right-clicky stuff in general would be nice.
Channels and Guide seem redundant. |  | Can we just have the Guide and get rid of Channels? For the moment, just make guide the first widget in the line.
Make Guide come first in widget list | Done | Pending decision on the above
TV Guide
Guide should roll up and down with the mouse wheel, not left to right. |  | Can do in a keymap, but not sure how in a skin. Requested.
Guide needs up/down/left/right buttons that appear with a mouse hover, like WMC |  | Autoscroll might also be OK (but not so aggressive as the My Addons list!)
Guide rows need to be a little bigger, also guide font